## Slide 1
General Updates
July 17, 2023

## Slide 2
Agenda
Subsequent Commission Redistricting Meeting Dates
Next Steps
Deadline Status

## Slide 3
Next Redistricting Commission Meeting Dates

## Slide 4
Possible Subsequent Redistricting
Commission Meeting Dates
Thursday, July 27, 2023; 5:30 pm*
Wednesday, Aug. 2, 2023; 1:00 pm
Friday, Aug. 4, 2023; 9:00 am

## Slide 5
Next Redistricting
Commission Meeting Dates
Tuesday, August 8, 2023; 1:00 pm
  Purpose: designate finalist map options
Tuesday, August 15, 2023; 1:00 pm
  Purpose: adopt final map from among the finalists
  *All subsequent meetings will be held at:
  Centennial Hall, 200 S. Cascade Ave.,
  Colorado Springs, CO 80903

## Slide 6
Next Steps

## Slide 7
August 8, 2023
  Vote to designate 3-4 finalist maps
  Last effective day to give additional direction
  Gives the public time to make comments about finalist maps
Recommend that you direct staff to run as full of an analysis as possible on any citizen submitted map between now and the next meeting.
Next Steps

## Slide 8
Deadline Status

## Slide 9
Aug 4, 2023
All five public hearings held (one in each Commissioner district)
July 24, 2023
Last day for public to submit plans via website
May 12, 2023
Create website for residents
to submit testimony & proposed maps
Deadline Status
Completed
Open
Completed

## Slide 10
August 15, 2023
Proposed date of
final adoption of plan
August 11, 2023
Last date for written public comment on proposals
August 8, 2023
Deadline for additional plans by redistricting commission
Deadline Status

## Slide 11
Questions?